## Deal Timeline
Deal Timeline — Gantt Tracker
PBG Capital Advisors · edit Start / End / % Complete and the bars redraw automatically
■ Planned |  | ■ Completed |  | ▮ This week
Task | Owner | Start | End | Days | % Done | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14
Phase 1 - Engagement & Preparation
Sign engagement letter | PBG / Client | 2026-08-03 | 2026-08-07 |  | 100%
Financial data collection & QoE | Client / PBG | 2026-08-03 | 2026-08-21 |  | 60%
Build financial model | PBG | 2026-08-10 | 2026-08-28 |  | 40%
Draft CIM & marketing materials | PBG | 2026-08-17 | 2026-09-04 |  | 15%
Phase 2 - Marketing & Outreach
Finalize buyer / lender list | PBG / Client | 2026-08-24 | 2026-09-04 |  | 0%
Distribute teaser & NDAs | PBG | 2026-08-31 | 2026-09-18 |  | 0%
Distribute CIM to signed parties | PBG | 2026-09-07 | 2026-09-25 |  | 0%
Management presentations | PBG / Client | 2026-09-14 | 2026-10-02 |  | 0%
Phase 3 - Bids & Negotiation
Receive IOIs / term sheets | Buyers | 2026-09-28 | 2026-10-09 |  | 0%
Evaluate & shortlist | PBG / Client | 2026-10-05 | 2026-10-16 |  | 0%
Negotiate & sign LOI | PBG / Legal | 2026-10-12 | 2026-10-30 |  | 0%
Phase 4 - Diligence & Documentation
Buyer due diligence | Buyer / Client | 2026-10-26 | 2026-11-27 |  | 0%
Draft definitive agreements | Legal | 2026-11-02 | 2026-11-27 |  | 0%
Negotiate purchase agreement | PBG / Legal | 2026-11-09 | 2026-12-04 |  | 0%
Phase 5 - Closing
Final approvals & funding | All parties | 2026-11-23 | 2026-12-11 |  | 0%
Sign & close | All parties | 2026-12-07 | 2026-12-18 |  | 0%
How to use
• Edit the Start and End dates (cols C–D) — the blue bars redraw automatically.
• Set % Done (col F) — the darker segment fills the completed portion of each bar.
• The amber column marks the week containing today's date (updates live via TODAY()).
• Add a task: insert a row, type the name/owner/dates; bars appear with no extra setup.
• Extend the timeline: the grid runs Aug 03 to Dec 14 (20 weeks).